## Sheet1
	11/21/23	11/22/23	11/23/24	11/24/23	11/27/23	11/28/23
Time Spent	4 hours	7 hours		5 hours	4 hours
Completed	landing page	1. Feed events into view, by user id (only grabs by client_id currently)2. Save Events to Database.	1. Can click events / 2. ctr + enter to make a new line in a cell libercalc / 3.		Finished writing update modal .

		Short term Goals
		1. Design new modal / 1.1 can update Events / 1.2 Tutor can See Events Scheduled / 1.3 Tutor approves or Denies Event / 1.4 Edit modal Size, Transitions / 2. back end for updating event / 3. Change color for Pending events to light blue / 4. Approved Events are dark blue / 5. Make calender smaller on screen

	11/27/23	11/28/23	11/29/23	11/30/23	12/01/23
Time Spent	4 hours	4 hours	nothing	4 hours	Deploy to production
worked on	Finished writing update modal	edits to modal, different view for different user			add type for admin to show availibility
	worked on update API request was stuck for hours			brings back tutors events
Completed				change color events (function in view)

	longer term: 1.new Database Migrations, rename stuff / 2. Fix Calender Time: Stored as UTC time / Displayed as Eastern	1. Design new modal / 1.1- should clear modal or make new one. / 1.2 Tutor can See Events Scheduled: / 1.3 Back end Validation for updating events / 1.4 Edit modal Size, Transitions / 3. Change color for Pending events to light blue / 4. Approved Events are Green / 5. Make Calender smaller on screen

	12/04/23	12/05/23	12/06/23
	6 hours	NOTHING
	Spent all day trying to get this site to work on Production
	solution was found by looking at different logging files / in public directory, and the actual project solution. / i had to build the front end and put the build file in / the public directory. moving the public directory from / the main project folder public caused a sht ton of issues. / still not sure if that is the best thing to do but i for now i'm doing it. / I had to edit index.php to get remap everything. / Edit hosts file on local pc to view site. WEBSITE IS UP		1 learn about emails / 2 get emails up and running on site. Holy@daytontutoring. Admin@daytontutorings.com / 3 get email notifications working / 3.1 email sign ups working / 4. remove chirps bullsht / 5 add holly's bio to the front landing page / 5. change dashboard to modified homepage / 6 add payment links / 7. modify everything for mobile friendliness. Now works but looks like / ass / Then Call it FINISHED---MAKE REVISIONS / Take Payment.