## Sheet1
	11/21/23	11/22/23	11/23/24	11/24/23	11/27/23	11/28/23
Time Spent	4 hours	7 hours		5 hours	4 hours
Completed	landing page	1. Feed events into view, by user id (only grabs by client_id currently)2. Save Events to Database.	1. Can click events / 2. ctr + enter to make a new line in a cell libercalc / 3.		Finished writing update modal .

		Short term Goals
		1. Design new modal / 1.1 can update Events / 1.2 Tutor can See Events Scheduled / 1.3 Tutor approves or Denies Event / 1.4 Edit modal Size, Transitions / 2. back end for updating event / 3. Change color for Pending events to light blue / 4. Approved Events are dark blue / 5. Make calender smaller on screen

	11/27/23	11/28/23	11/29/23	11/30/23	12/01/23
Time Spent	4 hours	4 hours	nothing	4 hours	Deploy to production
worked on	Finished writing update modal	edits to modal, different view for different user			add type for admin to show availibility
	worked on update API request was stuck for hours			brings back tutors events
Completed				change color events (function in view)

	longer term: 1.new Database Migrations, rename stuff / 2. Fix Calender Time: Stored as UTC time / Displayed as Eastern	1. Design new modal / 1.1- should clear modal or make new one. / 1.2 Tutor can See Events Scheduled: / 1.3 Back end Validation for updating events / 1.4 Edit modal Size, Transitions / 3. Change color for Pending events to light blue / 4. Approved Events are Green / 5. Make Calender smaller on screen

	12/04/23	12/05/23	12/06/23	12/07/23	12/08/23
	6 hours	NOTHING	2 hours	3 hours then got busy with work	got emails to send locally
	Spent all day trying to get this site to work on Production		removed chirps locally. Issue with Production build with vite on dev.	Emails are “sending” locally, don’t see / Local mail server. And message is messed up	they go to the local email server!!
	solution was found by looking at different logging files / in public directory, and the actual project solution. / i had to build the front end and put the build file in / the public directory. moving the public directory from / the main project folder public caused a sht ton of issues. / still not sure if that is the best thing to do but i for now i'm doing it. / I had to edit index.php to get remap everything. / Edit hosts file on local pc to view site. WEBSITE IS UP		Dragondoor@6665	set up email: / dig -x 49.24.222.67.in-adr.arpa / Returns ndxdomain. I think I think / I need to set the domain godaddy. / Sending email says: 550 invalid DNS MX	php artisan cache:clear / php artisan view:clear / php artisan config:clear / I spent hours on this stupid thing / Trying to get it to work, finally / I just commits my good good, / Stopped and restarted sail. And I / had a crazy permission error / About a logging file. Basically / after I ran the chowns, / And cleared cache my orginal / Problem was fixed.
	12/07/23	12/08/23	12/09/23		\
		add Privacy Policy / Add Terms of Use / Remove 10:00pm – 6-am times on calendar / Calendar Page check device look - > made it look / Just a bit better	1. Add Information of client and Tutor in calendar view / 2. click escape closes the modal / 3. add a type for Availibility / 4. Add Paypall page / 5. Add Toasts / 6. back end validation for availibilty / 7. sending reminder emails for Scheduled sessions / 8. showing already scheduled events as taken / 9. Show which tutor profile page you are on / 10. Add photo	1. save out notes
		3 hours	6 hours
			In PR Fixed 2 bugs on calender. Cleaned up device authenticated layout
			upgraded vite to version 5+ from 4+