## Sheet1
	11/21/23	11/22/23	11/23/24	11/24/23	11/27/23	11/28/23
Time Spent	4 hours	7 hours		5 hours	4 hours
Completed	landing page	1. Feed events into view, by user id (only grabs by client_id currently)2. Save Events to Database.	1. Can click events / 2. ctr + enter to make a new line in a cell libercalc / 3.		Finished writing update modal .

		Short term Goals
		1. Design new modal / 1.1 can update Events / 1.2 Tutor can See Events Scheduled / 1.3 Tutor approves or Denies Event / 1.4 Edit modal Size, Transitions / 2. back end for updating event / 3. Change color for Pending events to light blue / 4. Approved Events are dark blue / 5. Make calender smaller on screen

	11/27/23	11/28/23	11/29/23	11/30/23	12/01/23
Time Spent	4 hours	4 hours	nothing	4 hours	Deploy to production
worked on	Finished writing update modal	edits to modal, different view for different user			add type for admin to show availibility
	worked on update API request was stuck for hours			brings back tutors events
Completed				change color events (function in view)

	longer term: 1.new Database Migrations, rename stuff / 2. Fix Calender Time: Stored as UTC time / Displayed as Eastern	1. Design new modal / 1.1- should clear modal or make new one. / 1.2 Tutor can See Events Scheduled: / 1.3 Back end Validation for updating events / 1.4 Edit modal Size, Transitions / 3. Change color for Pending events to light blue / 4. Approved Events are Green / 5. Make Calender smaller on screen

	12/04/23	12/05/23	12/06/23	12/07/23	12/08/23
	6 hours	NOTHING	2 hours	3 hours then got busy with work	got emails to send locally
	Spent all day trying to get this site to work on Production		removed chirps locally. Issue with Production build with vite on dev.	Emails are “sending” locally, don’t see / Local mail server. And message is messed up	they go to the local email server!!
	solution was found by looking at different logging files / in public directory, and the actual project solution. / i had to build the front end and put the build file in / the public directory. moving the public directory from / the main project folder public caused a sht ton of issues. / still not sure if that is the best thing to do but i for now i'm doing it. / I had to edit index.php to get remap everything. / Edit hosts file on local pc to view site. WEBSITE IS UP		Dragondoor@6665	set up email: / dig -x 49.24.222.67.in-adr.arpa / Returns ndxdomain. I think I think / I need to set the domain godaddy. / Sending email says: 550 invalid DNS MX	php artisan cache:clear / php artisan view:clear / php artisan config:clear / I spent hours on this stupid thing / Trying to get it to work, finally / I just commits my good good, / Stopped and restarted sail. And I / had a crazy permission error / About a logging file. Basically / after I ran the chowns, / And cleared cache my orginal / Problem was fixed.
	12/07/23	12/08/23			\
		add Privacy Policy
		Add Terms of Use

## Sheet2
Dec 1, 2023	$0.42214	Dec 4, 2023	Dec 6, 2023
Nov 1, 2023	$0.41766	Nov 2, 2023	Nov 6, 2023
Oct 2, 2023	$0.41719	Oct 3, 2023	Oct 5, 2023
Sep 1, 2023	$0.45056	Sep 5, 2023	Sep 7, 2023
Aug 1, 2023	$0.3659	Aug 2, 2023	Aug 4, 2023
Jul 3, 2023	$0.3668	Jul 5, 2023	Jul 7, 2023
Jun 1, 2023	$0.35656	Jun 2, 2023	Jun 6, 2023
May 1, 2023	$0.48406	May 2, 2023	May 4, 2023
Apr 3, 2023	$0.45394	Apr 4, 2023	Apr 6, 2023
Mar 1, 2023	$0.43296	Mar 2, 2023	Mar 6, 2023
Feb 1, 2023	$0.44065	Feb 2, 2023	Feb 6, 2023
	4.60842
	41.85
	37.24158	49	11.75842